School of Governance and Society

Thesis Writing – Research work, Submission and Review Timelines

These timelines are mainly meant for Mphil students attending public policy program at the School of governance and society, UMT, Lahore.  The underlying purpose is to help students as well as supervisors to plan, appraise and evaluate progress of the research work. Subject to approval by the supervisor, these may be relaxed or amended as warranted on case to case basis.

|  |  | Time lines |  |
| --- | --- | --- | --- |
| Serial | Activity | Time allocation | Running time | Remarks |
|  | Choice of research supervisor by students | After completion of course work and soon after announcement of results the second semester | Week 1 | Academic coordinator will notify students to furnish their choices |
|  | First formal supervisor – student interaction to discuss selection of research topic | Within one week of selection of supervisor by the students | Week 2 | Timelines specifically the running time encompassing whole duration of the thesis writing should be changed into actual dates by the students after mutual agreement between supervisor and student(s) All submissions should be made on the last working day of the week |
|  | Finalization of research topic | Two weeks | Week 3-4 |  |
|  | Development of research proposal | Six weeks | Week 5-10 |  |
|  | Submission of first chapter | Four weeks | Week 11-14 |  |
|  | Review and corrections by the supervisor | One week | Week 15th |  |
|  | Submission of second chapter | Four weeks | Week 16-19 |  |
|  | Review and corrections by the supervisor | One week | Week 20th |  |
|  | Submission of third chapter | Four weeks | Week 21-24 |  |
|  | Review and corrections by the supervisor | One week | Week 25th |  |
|  | Submission of fourth chapter | Four weeks | Week 26-29 |  |
|  | Review and corrections by the supervisor | One week | Week 30th |  |
|  | Submission of conclusion and recommendations | One week | Week 31st |  |
|  | Submission of first draft of research thesis | - | Week 32nd |  |
|  | Review of first draft and discussion | One week | Week 33rd |  |
|  | Submission of second draft and discussion | One week | Week 34th |  |
|  | Submission of final thesis | Two weeks | Week 36th |  |